FDE PRACTICE ACTIVATION · ADDENDUM 10 · TRACKING SHEET

# FDE 30 / 60 / 90 — OKR Scorecard

Fill Actual at each horizon close · score every Key Result 0.0–1.0 · a horizon’s score is the mean of its KRs

How to use.  This is the companion tracking grid to Addendum 09. The Key Results and Targets are fixed; the three right-hand columns are for you to complete. At each 30 / 60 / 90 checkpoint, record the Actual, score the KR 0.0–1.0 (the fraction of target achieved — binary KRs score 0 or 1), and mark its status. Average a horizon’s KR scores for its headline number. Treat ~0.7 as on-track; a steady 1.0 means the targets were set too low.

| ● Green — score ≥ 0.70 (on-track) | ● Amber — 0.40–0.69 (at-risk) | ● Red — < 0.40 (off-track) |
| --- | --- | --- |

| DAYS 0–30 · Land & Charter Objective: Establish FDE as a credible, chartered practice anchored by a live customer reference. | HORIZON SCORE ______ / 1.0 |
| --- | --- |

| # | Key Result (outcome) | Target | Actual | Score | R/A/G |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Modutecture formalized as first reference; FDE Charter v1 signed. | Signed + ref. |  |  |  |
| 1.2 | Target accounts identified and scored for embedded-FDE fit. | 3–5 accounts |  |  |  |
| 1.3 | FDE Charter v1 published (definition, FDE↔GCC, Loop™ v1, metrics). | Published |  |  |  |
| 1.4 | Time-to-First-Value baseline established on the pilot. | < 14 days |  |  |  |

| DAYS 31–60 · Codify & Prove Objective: Convert one success into a repeatable, staffed practice that demonstrably transfers. | HORIZON SCORE ______ / 1.0 |
| --- | --- |

| # | Key Result (outcome) | Target | Actual | Score | R/A/G |
| --- | --- | --- | --- | --- | --- |
| 2.1 | FDE Loop™ Cookbook + Landing Runbook published (teachable, branded). | Both published |  |  |  |
| 2.2 | FDEs identified / onboarding, each paired with an offshore pod. | 2–3 FDEs |  |  |  |
| 2.3 | Second account landed using the FDE Loop™ (proves transfer). | 1 account |  |  |  |
| 2.4 | Client-Authored Spec Ratio on the pilot by end of Month 2. | > 60% |  |  |  |
| 2.5 | Agentic PR Merge Rate / Human Intervention Rate held flat. | > 90% / < 2 per 1k |  |  |  |

| DAYS 61–90 · Productize & Scale Objective: Make FDE a named, sellable, scaling practice line with a pipeline, dashboard, and co-sell. | HORIZON SCORE ______ / 1.0 |
| --- | --- |

| # | Key Result (outcome) | Target | Actual | Score | R/A/G |
| --- | --- | --- | --- | --- | --- |
| 3.1 | “StatusNeo FDE” live as a named practice on the site and sales motion. | Live |  |  |  |
| 3.2 | FDE practice dashboard live (accounts, expansion, pull-ratio, trust, NPS). | Reporting |  |  |  |
| 3.3 | Reference accounts documented. | 2–4 accounts |  |  |  |
| 3.4 | Co-sell enablement delivered to all regions (WC, EC, EMEA, APAC). | All regions |  |  |  |
| 3.5 | System Adoption Velocity / Platform Contribution Rate (Spoke→Hub). | > 75% / ≥ 2 |  |  |  |

OVERALL ROLLUP

| Days 0–30 ____ / 1.0 | Days 31–60 ____ / 1.0 | Days 61–90 ____ / 1.0 | 90-DAY MEAN ____ / 1.0 |
| --- | --- | --- | --- |

BEFORE YOU COMMIT TO THESE TARGETS Several targets here — TTFV < 14 days, Spec Ratio > 60%, PR Merge > 90%, and the economics behind them — originate from June-2026 source briefings and are pending verification. A scorecard turns a target into a commitment you will be measured against. Confirm each number you are willing to own before this grid goes to the sponsor; adjust any that are aspirational rather than agreed.

The StatusNeo Agentic FDE Practice · Addendum 10 · OKR Scorecard · companion to Addendum 09 · June 2026